## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | <optional> |  |  |  |  | Project Name: | <optional>
National Center: |  |  | <required> |  |  |  |  | National Center: | <required>
Project Manager Name: |  |  | <required> |  |  |  |  | Project Manager Name: | <required>
Project Description: |  |  | <required> |  |  |  |  | Project Description: | <required>
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
| Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
| Open | Medium | Medium | Yellow | Ongoing build or modifications to the source code would be pushed on GitHub. While pushing the code, if the GitHub issues are not addressed properly. | Unauthorized or incorrect code commits (e.g., push or force-push) to inappropriate branches, combined with inadequate version control error handling, may result in codebase corruption. This directly impacts build stability and may cause pipeline failures. | Schedule Data/Information Project Resources Change Management |  |  | Mitigation
| Open | Low | Low | Green | Lack of technical skillsets required for the development of the program. | This risk can lead to deviation from defined project deliverables, resulting in incomplete or inconsistent outputs. It may also negatively affect the project scope and cost baseline, potentially hindering achievement of intended project objectives. | Project Management Technology Obsolescence Schedule |  |  | Mitigation
[5 empty] | Not meeting the expected outcomes of the project. | The financial plan may be adversely affected, potentially exceeding allocated resources. This could impair timely achievement of project milestones and result in delays to the final delivery. | Business Strategic |  |  | Transfer
[5 empty] | Inaccurate estimation of the project budget. | Budgetary overruns may occur, exceeding the estimated expenditure, potentially requiring the project group to absorb losses. Such scenarios may lead to slippage in timeline and delayed realization of project deliverables. | Business Overall Project Failure |  |  | Contingency
[5 empty] | Improper implementation of a fuctionality in the project. | Incorrect or incomplete implementation of key functionalities may impair the reliability and completeness of expected outcomes. This may also compromise system build integrity due to code compilation or runtime errors. | Overall Project Failure Reliability of Systems Dependencies/Interoperability |  |  | Mitigation
[5 empty] | Issues or challenges in the API integration. | Overall application fidelity may degrade, leading to operational inaccuracies. There is increased likelihood of false-positive occurrences, potentially breaching acceptable quality assurance thresholds. | Technology Dependencies/Interoperability Surety Considerations |  |  | Mitigation
[5 empty] | Issues or challenges in configuration of the application running on various systems with different specifications. | Environmental constraints or partial functionality failures may negatively impact user experience. This may limit end-user adoption and reduce potential for community or stakeholder engagement. | Reliability of Systems Technical Obsolescence |  |  | Mitigation
[5 empty] | Difference in the modes of communication between team members. Some members may be attending the discussions offline while some may be working remotely. | The project team may encounter challenges in aligning deliverables with stakeholder expectations. This misalignment may introduce delays in achieving key deliverables or critical milestones. | Schedule Project Manegement Strategic |  |  | Avoidance
[5 empty] | Gaps in understanding the expectations of the project. Not all members would work simultaneously on the same code or assessment. | Extended delivery timelines and compromised project outcomes may result from unresolved code conflicts. Concurrent updates by multiple contributors on a shared codebase may cause integration issues, thereby increasing rework and schedule risk. | Business Schedule |  |  | Avoidance
[5 empty] | Lack of segregation of duties. Lacking accountability on a particular aspect of the project. | Project results may be inconsistent or misaligned with defined goals. Disparities in team member contribution levels may emerge, impacting team morale. Both financial and scheduling baselines may be adversely affected. | Project Management Schedule |  |  | Contingency
[5 empty] | Implementating API keys or other sensitive data in plain text. (source code review/inspect elements) |  | Security |  |  | Acceptance
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources