## Report
[Project Title]
Earned Value Analysis Report
| Prepared By: | Asha Pradeep, Astha Sharma
| Date: | 23rd April 2025
[42]
For Period:
Summary:
[Use this space to write a brief summary or to record specific observations or notes]
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Project Management | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Creating Risk Management | 1520 | 1520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Project Budget Plan | 2280 | 1140 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Drafting Test Document Ten | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | Project Management Plan | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | Project Plan | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | Development Plan | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | Application Development | 2280 | 701.54 | 701.54 | 701.54 | 175.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | API Integration | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Functionality 1 | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Functionality 2 | 2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Beta Release | 35760 | 0 | 0 | 0 | 35760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total PV | 55960 | 12961.54 | 3641.54 | 3101.54 | 35935.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Budgeted Cost | 55840 | 13161.54 | 3641.54 | 3101.54 | 35935.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Planned Value (PV) | 69001.54 | 72643.08 | 75744.62 | 111680 | 111680 | 111680 | 111680 | 111680 | 111680 | 111680 | 111680 | 111680
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 13623.08 | 33758.46 | 59266.15 | 92878.46 | 128983.08 | 167580 | 208669.23 | 251004.61 | 293339.99 | 335675.37 | 378010.75 | 420346.13
|  | Cumulative Earned Value (EV) | 752713566 | 847676668 | 975813402 | 3921455379.2 | 4027165024 | 4130954668.8 | 4231244800 | 4231244800 | 4231244800 | 4231244800 | 4231244800 | 4231244800
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 752699942.92 | 847642909.54 | 975754135.85 | 3921362500.74 | 4027036040.92 | 4130787088.8 | 4231036130.77 | 4230993795.39 | 4230951460.01 | 4230909124.63 | 4230866789.25 | 4230824453.87
|  | Schedule Variance (SV = EV - PV) | 752644564.46 | 847604024.92 | 975737657.38 | 3921343699.2 | 4027053344 | 4130842988.8 | 4231133120 | 4231133120 | 4231133120 | 4231133120 | 4231133120 | 4231133120
|  | Cost Performance Index (CPI = EV/AC) | 55252.8185 | 25110.0515 | 16464.9366 | 42221.3652 | 31222.4287 | 24650.6425 | 20277.2819 | 16857.2394 | 14424.3708 | 12605.1691 | 11193.451 | 10066.0967
|  | Schedule Performance Index (SPI = EV/PV) | 10908.6488 | 11669.0629 | 12882.9401 | 35113.3182 | 36059.8587 | 36989.2073 | 37887.2206 | 37887.2206 | 37887.2206 | 37887.2206 | 37887.2206 | 37887.2206
|  | Estimated Cost at Completion (EAC) | 1.0106 | 2.2238 | 3.3914 | 1.3226 | 1.7885 | 2.2653 | 2.7538 | 3.3125 | 3.8712 | 4.4299 | 4.9886 | 5.5473
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Project Management | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
1.2 | Creating Risk Management | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520
1.3 | Project Budget Plan | 2280 | 1140 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280
1.4 | Drafting Test Document Ten | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800
1.5 | Project Management Plan | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
1.6 | Project Plan | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
1.7 | Development Plan | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
1.8 | Application Development | 2280 | 350.77 | 701.54 | 1052.31 | 1403.08 | 1753.85 | 2104.62 | 2280 | 2280 | 2280 | 2280 | 2280 | 2280
1.9 | API Integration | 400 | 266.67 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400
2 | Functionality 1 | 1800 | 0 | 300 | 600 | 900 | 1200 | 1500 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800
2.1 | Functionality 2 | 2400 | 0 | 0 | 800 | 1600 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
2.2 | Beta Release | 35760 | 0 | 0 | 0 | 35760 | 35760 | 35760 | 35760 | 35760 | 35760 | 35760 | 35760 | 35760
| Cumulative EV | 55960 | 12977.44 | 14603.08 | 16834.62 | 46563.08 | 48393.85 | 50224.62 | 52000 | 52000 | 52000 | 52000 | 52000 | 52000
|  | Cumulative EV | 752713566 | 847676668 | 975813402 | 3921455379.2 | 4027165024 | 4130954668.8 | 4231244800 | 4231244800 | 4231244800 | 4231244800 | 4231244800 | 4231244800

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Project Management |  | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Creating Risk Management |  | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Project Budget Plan |  | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Drafting Test Document Ten |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | Project Management Plan |  | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | Project Plan |  | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | Development Plan |  | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | Application Development |  | 623.08 | 2492.31 | 2492.31 | 2492.31 | 2492.31 | 2492.31 | 2492.31 | 1246.15 | 0 | 0 | 0 | 0
1.9 | API Integration |  | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Functionality 1 |  | 0 | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Functionality 2 |  | 0 | 0 | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Beta Release |  | 0 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insert new rows above this one |  |  | 13623.08 | 6512.31 | 5372.31 | 8104.62 | 2492.31 | 2492.31 | 2492.31 | 1246.15 | 0 | 0 | 0 | 0
|  | Total Actual Cost | 13623.08 | 20135.38 | 25507.69 | 33612.31 | 36104.62 | 38596.92 | 41089.23 | 42335.38 | 42335.38 | 42335.38 | 42335.38 | 42335.38
|  | Cumulative Actual Cost (AC) | 13623.08 | 33758.46 | 59266.15 | 92878.46 | 128983.08 | 167580 | 208669.23 | 251004.61 | 293339.99 | 335675.37 | 378010.75 | 420346.13